## WBSData
WBS | Name | 2 | Start | Finish | Duration | Optimista | Mas Probable | Pesimista | des. Estandar | Varianza
1 | Importaciones SA de CV |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 115.3333
1.1 | Equipo Computo |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 9.6667
1.1.1 | Adquisicion |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 7.3333
1.1.1.1 | Cotizar equipo |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 2.1667 | 1 | 2 | 4 | 0.5 | 0.25
1.1.1.2 | Revisar cotizaciones | 5 | 2019-09-11 08:00 | 2019-09-11 17:00 | 3.1667 | 2 | 3 | 5 | 0.5 | 0.25
1.1.1.3 | Realizar compra | 6 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2 | 1 | 2 | 3 | 0.33333 | 0.11111
1.1.2 | Instalacion |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 2.3333
1.1.2.1 | Inst. PC 1 | 7,16,21 | 2019-09-11 08:00 | 2019-09-11 17:00 | 1.1667 | 1 | 1 | 2 | 0.16667 | 0.027778
1.1.2.2 | Inst. PC2 | 9,16,21 | 2019-09-11 08:00 | 2019-09-11 17:00 | 1.1667 | 1 | 1 | 2 | 0.16667 | 0.027778
1.2 | Instalaciones |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 35.6667 |  |  |  | 0 | 0
1.2.1 | Instalacion Electrica |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 17.8333
1.2.1.1 | Revision de Inst Electrica |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 2.1667 | 1 | 2 | 4 | 0.5 | 0.25
1.2.1.2 | Generar lista de materiales | 13 | 2019-09-11 08:00 | 2019-09-11 17:00 | 3 | 2 | 3 | 4 | 0.33333 | 0.11111
1.2.1.3 | Realizar compras | 14 | 2019-09-11 08:00 | 2019-09-11 17:00 | 4.1667 | 2 | 4 | 7 | 0.83333 | 0.69444
1.2.1.4 | Realizar instalacion | 15 | 2019-09-11 08:00 | 2019-09-11 17:00 | 8.5 | 5 | 8 | 14 | 1.5 | 2.25
1.2.2 | Instalacion de Red |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 17.8333
1.2.2.1 | Revision de Red | 16 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2.1667 | 1 | 2 | 4 | 0.5 | 0.25
1.2.2.2 | Generar lista de materiales | 18 | 2019-09-11 08:00 | 2019-09-11 17:00 | 3 | 2 | 3 | 4 | 0.33333 | 0.11111
1.2.2.3 | Realizar compras | 19 | 2019-09-11 08:00 | 2019-09-11 17:00 | 4.1667 | 2 | 4 | 7 | 0.83333 | 0.69444
1.2.2.4 | Realizar instalacion | 20 | 2019-09-11 08:00 | 2019-09-11 17:00 | 8.5 | 5 | 8 | 14 | 1.5 | 2.25
1.3 | Desarrollo SW |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 70
1.3.1 | Requerimientos |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 6
1.3.1.1 | Modulo Pedidos | 20 | 2019-09-11 08:00 | 2019-09-11 17:00 | 3 | 2 | 3 | 4 | 0.33333 | 0.11111
1.3.1.2 | Modulo Envios | 24 | 2019-09-11 08:00 | 2019-09-11 17:00 | 3 | 2 | 3 | 4 | 0.33333 | 0.11111
1.3.2 | Analisis y diseño |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 15.3333
1.3.2.1 | Aquitectura de la aplicacion | 25 | 2019-09-11 08:00 | 2019-09-11 17:00 | 5 | 3 | 5 | 7 | 0.66667 | 0.44444
1.3.2.2 | Base de datos | 27 | 2019-09-11 08:00 | 2019-09-11 17:00 | 3 | 1 | 3 | 5 | 0.66667 | 0.44444
1.3.2.3 | Diseño de interfaz de usuario | 28 | 2019-09-11 08:00 | 2019-09-11 17:00 | 7.3333 | 4 | 7 | 12 | 1.3333 | 1.7778
1.3.3 | Desarrollo |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 18.6667
1.3.3.1 | Implementar arquitecrtura | 29 | 2019-09-11 08:00 | 2019-09-11 17:00 | 6 | 2 | 5 | 14 | 2 | 4
1.3.3.2 | Construir BD | 31 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2 | 1 | 2 | 3 | 0.33333 | 0.11111
1.3.3.3 | Desarrollar GUI |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 10.6667
1.3.3.3.1 | Mod. Pedidos | 32 | 2019-09-11 08:00 | 2019-09-11 17:00 | 5.3333 | 3 | 5 | 9 | 1 | 1
1.3.3.3.2 | Mod Envios | 34 | 2019-09-11 08:00 | 2019-09-11 17:00 | 5.3333 | 3 | 5 | 9 | 1 | 1
1.3.4 | Pruebas |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 24
1.3.4.1 | P.U Mod. Pedidos | 34 | 2019-09-11 08:00 | 2019-09-11 17:00 | 7.6667 | 4 | 7 | 14 | 1.6667 | 2.7778
1.3.4.2 | P.U Mod. Envios | 35 | 2019-09-11 08:00 | 2019-09-11 17:00 | 7.6667 | 4 | 7 | 14 | 1.6667 | 2.7778
1.3.4.3 | Pruebas Integracion | 37,38 | 2019-09-11 08:00 | 2019-09-11 17:00 | 8.6667 | 6 | 8 | 14 | 1.3333 | 1.7778
1.3.5 | Despliegue |  | 2019-09-11 08:00 | 2019-09-11 17:00 | 6
1.3.5.1 | Config. Servidor | 39 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2 | 1 | 2 | 3 | 0.33333 | 0.11111
1.3.5.2 | Config. Cliente 1 | 9,39 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2 | 1 | 2 | 3 | 0.33333 | 0.11111
1.3.5.3 | Config. Cliente 2 | 10,39 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2 | 1 | 2 | 3 | 0.33333 | 0.11111
[9 empty] | Des. Estandar Gral | 4.8933
[8 empty] | Mayor tiempo probable |  | 125.1199
[8 empty] | Menor tiempo probable |  | 105.5467
10.67

## Hoja2
Ejercicio 1 | OP | MP | PES | PERT | σ | σ² | Ejercicio 2 | OP | MP | PES | PERT | σ | σ²
A | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25 | A | 3 | 4 | 6 | 4.1667 | 0.5 | 0.25
B | 1 | 2 | 3 | 2 | 0.33333 | 0.11111 | B | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
C | 2 | 4 | 6 | 4 | 0.66667 | 0.44444 | C | 0.5 | 1 | 3 | 1.25 | 0.41667 | 0.17361
D | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778 | D | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
E | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778 | E | 2 | 3 | 6 | 3.3333 | 0.66667 | 0.44444
F | 2 | 3 | 4 | 3 | 0.33333 | 0.11111 | F | 1 | 4 | 8 | 4.1667 | 1.1667 | 1.3611
G | 1 | 1 | 1 | 1 | 0 | 0 | G | 2 | 4 | 10 | 4.6667 | 1.3333 | 1.7778
H | 1 | 1 | 1 | 1 | 0 | 0 | H | 1 | 2 | 5 | 2.3333 | 0.66667 | 0.44444
I | 5 | 8 | 15 | 8.6667 | 1.6667 | 2.7778 | I | 1 | 4 | 7 | 4 | 1 | 1
J | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25 | J | 1 | 2 | 5 | 2.3333 | 0.66667 | 0.44444
K | 3 | 5 | 7 | 5 | 0.66667 | 0.44444 | K | 2 | 4 | 8 | 4.3333 | 1 | 1
[7 empty] | L | 0.5 | 1 | 4 | 1.4167 | 0.58333 | 0.34028
|  |  | DURACION DEL PROYECTO |  |  | 32.3333 | M | 1 | 3 | 5 | 3 | 0.66667 | 0.44444
|  |  | DESVIACION ESTANDAR GRAL |  |  | 2.1082 |  |  |  |  | 40.3333
2.8602
Ejercicio 1 | OP | MP | PES | PERT | σ | σ² | Ejercicio 2 | OP | MP | PES | PERT | σ | σ²
A | 2 | 3 | 5 | 3.16 | 0.5 | 0.25 | A | 3 | 4 | 6 | 4.16 | 0.5 | 0.25
B | 1 | 2 | 3 | 2 | 0.33333 | 0.1 | B | 2 | 3 | 5 | 3.16 | 0.5 | 0.25
C | 2 | 4 | 6 | 4 | 0.66 | 0.43 | C | 0.5 | 1 | 3 | 1.25 | 0.41 | 0.16
D | 1 | 1 | 2 | 1.16 | 0.16 | 0.02 | D | 1 | 2 | 4 | 2.16 | 0.5 | 0.25
E | 1 | 1 | 2 | 1.16 | 0.16 | 0.02 | E | 2 | 3 | 6 | 3.33 | 0.66 | 0.43
F | 2 | 3 | 4 | 3 | 0.33333 | 0.1 | F | 1 | 4 | 8 | 4.16 | 1.16 | 1.34
G | 1 | 1 | 1 | 1 | 0 | 0 | G | 2 | 4 | 10 | 4.66 | 1.33 | 1.76
H | 1 | 1 | 1 | 1 | 0 | 0 | H | 1 | 2 | 5 | 2.33 | 0.66 | 0.43
I | 5 | 8 | 15 | 8.66 | 1.66 | 2.75 | I | 1 | 4 | 7 | 4 | 1 | 1
J | 1 | 2 | 4 | 2.16 | 0.5 | 0.25 | J | 1 | 2 | 5 | 2.33 | 0.66 | 0.43
K | 3 | 5 | 7 | 5 | 0.66 | 0.43 | K | 2 | 4 | 8 | 4.33 | 1 | 1
[7 empty] | L | 0.5 | 1 | 4 | 1.41 | 0.58 | 0.33
|  |  | DURACION DEL PROYECTO |  |  | 32.3 | M | 1 | 3 | 5 | 3 | 0.66 | 0.43 | 8.06
|  |  | DESVIACION ESTANDAR GRAL |  |  | 2.0857
[10 empty] | DURACION DEL PROYECTO |  |  | 40.28
[10 empty] | DESVIACION ESTANDAR GRAL |  |  | 2.839
2.839

## TempData (hidden)
Work- | Baseline Work- | Actual Work- | Work Variance- | Remaining Work- | Cost- | Baseline Cost- | Actual Cost- | Fixed Cost- | Cost Variance- | Remaining Cost- | BCWP- | BCWS- | SV- | Name+ | Notes+ | WBS+ | Constraint Type+ | Constraint Date= | Critical+ | Delay- | Free Slack- | Total Slack- | ID- | Milestone+ | Priority+ | Subproject+ | Baseline Duration- | Actual Duration- | Duration- | Duration Variance- | Remaining Duration- | Percent Complete-[% Complete] | Percent Work Complete-[% Work Complete] | Start= | Finish= | Early Start= | Early Finish= | Late Start= | Late Finish= | Actual Start= | Actual Finish= | Baseline Start= | Baseline Finish= | Start Variance- | Finish Variance- | Predecessors+ | Successors+ | Resource Names+ | Resource Initials+ | Text1+ | Start1= | Finish1= | Text2+ | Start2= | Finish2= | Text3+ | Start3= | Finish3= | Text4+ | Start4= | Finish4= | Text5+ | Start5= | Finish5= | Text6+ | Text7+ | Text8+ | Text9+ | Text10+ | Marked+ | Flag1+ | Flag2+ | Flag3+ | Flag4+ | Flag5+ | Flag6+ | Flag7+ | Flag8+ | Flag9+ | Flag10+ | Rollup+ | CV- | Project+ | Outline Level- | Unique ID- | Number1- | Number2- | Number3- | Number4- | Number5- | Summary+ | Created= | Unique ID Predecessors+ | Unique ID Successors+ | Objects- | Linked Fields+ | Resume= | Stop= | Resume No Earlier Than= | Outline Number+ | Duration1- | Duration2- | Duration3- | Cost1- | Cost2- | Cost3- | Hide Bar+ | Confirmed+ | Update Needed+ | Contact+ | Resource Group+ | ACWP- | Type+ | Recurring+ | Effort Driven+ | Overtime Work- | Actual Overtime Work- | Remaining Overtime Work- | Regular Work- | Overtime Cost- | Actual Overtime Cost- | Remaining Overtime Cost- | Fixed Cost Accrual+ | Hyperlink+ | Hyperlink Address+ | Hyperlink SubAddress+ | Hyperlink Href+ | Assignment+ | Overallocated+ | External Task+ | Subproject Read Only+ | Response Pending+ | TeamStatus Pending+ | Leveling Can Split+ | Level Assignments+ | Work Contour+ | Cost4- | Cost5- | Cost6- | Cost7- | Cost8- | Cost9- | Cost10- | Date1= | Date2= | Date3= | Date4= | Date5= | Date6= | Date7= | Date8= | Date9= | Date10= | Duration4- | Duration5- | Duration6- | Duration7- | Duration8- | Duration9- | Duration10- | Start6= | Finish6= | Start7= | Finish7= | Start8= | Finish8= | Start9= | Finish9= | Start10= | Finish10= | Flag11+ | Flag12+ | Flag13+ | Flag14+ | Flag15+ | Flag16+ | Flag17+ | Flag18+ | Flag19+ | Flag20+ | Number6- | Number7- | Number8- | Number9- | Number10- | Number11- | Number12- | Number13- | Number14- | Number15- | Number16- | Number17- | Number18- | Number19- | Number20- | Text11+ | Text12+ | Text13+ | Text14+ | Text15+ | Text16+ | Text17+ | Text18+ | Text19+ | Text20+ | Text21+ | Text22+ | Text23+ | Text24+ | Text25+ | Text26+ | Text27+ | Text28+ | Text29+ | Text30+ | Assignment Delay- | Assignment Units- | Cost Rate Table+ | Preleveled Start= | Preleveled Finish= | WBS Predecessors+ | WBS Successors+ | Deadline= | Outline Code1+ | Outline Code2+ | Outline Code3+ | Outline Code4+ | Outline Code5+ | Outline Code6+ | Outline Code7+ | Outline Code8+ | Outline Code9+ | Outline Code10+ | Status+ | Physical Percent Complete-[Physical % Complete] | SVPercent- | CVPercent- | Calendar+
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Importaciones SA de CV |  | 1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 1 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Equipo Computo |  | 1.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 2 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Adquisicion |  | 1.1.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 3 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 28 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cotizar equipo |  | 1.1.1.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 4 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 30 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.1.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Revisar cotizaciones |  | 1.1.1.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 5 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 31 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.1.1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Realizar compra |  | 1.1.1.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 6 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 34 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.1.1.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Instalacion |  | 1.1.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 7 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 29 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Inst. PC 1 |  | 1.1.2.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 8 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 35 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.1.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Inst. PC2 |  | 1.1.2.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 9 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 36 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.1.2.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Instalaciones |  | 1.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 10 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 3 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Instalacion de Red |  | 1.2.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 11 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 37 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Revision de Red |  | 1.2.1.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 12 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 39 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generar lista de materiales |  | 1.2.1.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 13 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 40 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Realizar compras |  | 1.2.1.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 14 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 41 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.1.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Realizar instalacion |  | 1.2.1.4 | Lo antes posible |  | Sí | 0d | 0d | 0d | 15 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 42 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.1.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Instalacion Electrica |  | 1.2.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 16 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 38 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.2.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Revision de Inst Electrica |  | 1.2.2.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 17 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 43 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generar lista de materiales |  | 1.2.2.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 18 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 44 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.2.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Realizar compras |  | 1.2.2.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 19 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 45 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.2.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Realizar instalacion |  | 1.2.2.4 | Lo antes posible |  | Sí | 0d | 0d | 0d | 20 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 46 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.2.2.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Desarrollo SW |  | 1.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 21 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 27 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Requerimientos |  | 1.3.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 22 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 47 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.3.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Modulo Pedidos |  | 1.3.1.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 23 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 51 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Modulo Envios |  | 1.3.1.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 24 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 52 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Analisis y diseño |  | 1.3.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 25 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 48 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.3.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Aquitectura de la aplicacion |  | 1.3.2.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 26 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 53 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Base de datos |  | 1.3.2.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 27 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 54 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.2.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Diseño de interfaz de usuario |  | 1.3.2.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 28 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 55 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.2.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Desarrollo |  | 1.3.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 29 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 49 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.3.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Implementar arquitecrtura |  | 1.3.3.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 30 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 56 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.3.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construir BD |  | 1.3.3.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 31 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 57 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.3.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Desarrollar GUI |  | 1.3.3.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 32 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 58 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.3.3.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mod. Pedidos |  | 1.3.3.3.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 33 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 5 | 59 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.3.3.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mod Envios |  | 1.3.3.3.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 34 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 5 | 60 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.3.3.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pruebas |  | 1.3.4 | Lo antes posible |  | Sí | 0d | 0d | 0d | 35 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 50 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.3.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P.U Mod. Pedidos |  | 1.3.4.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 36 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 61 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.4.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P.U Mod. Envios |  | 1.3.4.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 37 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 62 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.4.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pruebas Integracion |  | 1.3.4.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 38 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 64 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.4.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Despliegue |  | 1.3.5 | Lo antes posible |  | Sí | 0d | 0d | 0d | 39 | No | Mínima |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 63 | 0 | 0 | 0 | 0 | 0 | Sí |  |  |  | 0 | No |  |  |  | 1.3.5 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Config. Servidor |  | 1.3.5.1 | Lo antes posible |  | Sí | 0d | 0d | 0d | 40 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 65 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.5.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Config. Cliente 1 |  | 1.3.5.2 | Lo antes posible |  | Sí | 0d | 0d | 0d | 41 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 66 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.5.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Config. Cliente 2 |  | 1.3.5.3 | Lo antes posible |  | Sí | 0d | 0d | 0d | 42 | No | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 | 2019-09-11 08:00 | 2019-09-11 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 67 | 0 | 0 | 0 | 0 | 0 | No |  |  |  | 0 | No |  |  |  | 1.3.5.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Unidades fijas | No | Sí | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorrateo |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)